## Overview
Rodgers Ski & Sport — Marketing Plan Project Roadmap
Built from Rodgers_Ski_Sport_Marketing_Plan_v2_Full.docx (June 2026)
What's in this workbook
90-Day Launch Roadmap (Gantt) | Week-by-week execution plan from kickoff (July 6, 2026) through the Fall Tent Sale launch — website rebuild, email/social infrastructure, reservation system, and Tent Sale campaign.
Annual Marketing Calendar (Gantt) | 12-month campaign calendar (Jun 2026 – Apr 2027) showing each seasonal campaign window and its prep lead time.
Priorities Checklist | The plan's 14 sequenced priorities (Part II), with owner and suggested timing, for tracking approvals and kickoff items.
How to use it
Start dates | Edit the Start Date / End Date cells (light yellow) on the Gantt tabs — the bars are driven by conditional formatting, so they will move automatically.
Status | Use the Status column on the Task List tabs to track progress (Not Started / In Progress / Done / Blocked).
Owners | Owner values map to the roles defined in the plan: Ownership (Sean), Mike (Marketing Director/Consultant), Coordinator (Kaelyn), Waterside (website dev team).
Legend
Active execution window
Prep / lead-time window
Milestone / launch date
Editable input cell (dates, owners)
Summer Tent Sale (Jul 25–Aug 9) — kept distinct from the Fall Tent Sale

## 90-Day Roadmap (Gantt)
Rodgers Ski & Sport — 90-Day Marketing Launch Roadmap (Kickoff → Fall Tent Sale)
Phase | Task | Owner | Start Date | End Date | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12
Pre-Launch | Hand over materials: photos, customer lists, print materials, dealer agreements, memberships | Ownership | 2026-07-06 | 2026-07-12
Pre-Launch | Grant logins/admin access for every account; verify Google Business Profiles (both locations) | Ownership | 2026-07-06 | 2026-07-12
Pre-Launch | Approve final branding (logo, colors, fonts, voice, tagline) and lock promo calendar | Mike / Ownership | 2026-07-06 | 2026-07-12
Website | Lock platform, sitemap, content owners, launch-blocking features, approval process | Mike / Waterside | 2026-07-06 | 2026-07-12
Weeks 3 | Summer Tent Sale prep: promote via existing site/social/email (new systems not yet live) | Coordinator / Ownership | 2026-07-06 | 2026-07-24
Weeks 1-2 | Access & audit: catalog materials, confirm account access, fix listing data (Google/Yelp/Apple Maps/Bing) | Coordinator | 2026-07-13 | 2026-07-19
Weeks 1-2 | Social consolidation: confirm accounts to keep, secure handle, merge Facebook pages, redirect duplicates | Coordinator | 2026-07-20 | 2026-07-26
Weeks 3-5 | MILESTONE: Summer Tent Sale runs (Jul 25 - Aug 9) — distinct from the Fall Tent Sale | Ownership | 2026-07-25 | 2026-08-09
Weeks 3-4 | Email foundation: configure platform, signup form, welcome flow, list segments | Coordinator / Mike | 2026-07-27 | 2026-08-04
Weeks 3-4 | Brand kit into templates: Canva templates, content calendar template, first month of posts drafted | Coordinator / Mike | 2026-08-05 | 2026-08-27
Website | Build pages and load content from asset inventory | Waterside | 2026-08-11 | 2026-08-18
Weeks 5-6 | Regular posting & Google rhythm: 4 posts/week live, welcome flow on, weekly Google posts, review asks begin | Coordinator | 2026-08-17 | 2026-08-31
Weeks 7-8 | Summer outreach & content bank: bike/e-bike/tune-up content, Eastern Trail Alliance outreach, shoot summer bank | Coordinator | 2026-08-24 | 2026-08-30
Weeks 5-6 | Rental reservations: build form, auto-confirmation email, staging/pickup process, test a booking | Coordinator | 2026-08-31 | 2026-09-04
Website | Review, SEO setup, analytics (GA4), mobile testing, forms, redirects | Waterside / Mike | 2026-08-31 | 2026-09-30
Website | Soft launch: listing alignment, staff review, fix list | Waterside / Coordinator | 2026-08-31 | 2026-09-30
Website | Final QA and staff walkthrough before go-live | Mike / Waterside / Ownership | 2026-08-31 | 2026-09-30
Website | MILESTONE: Website fully live (by end of August, ahead of Fall Tent Sale) | Waterside | 2026-08-31 | 2026-09-30
Weeks 11-12 | Tent Sale campaign launch: countdown content, email sequence, Google posts, KPI dashboard live | Coordinator / Mike / Ownership | 2026-08-31 | 2026-09-17
Weeks 7-8 | Winter flows & Tent Sale map: tune-up reminder, Junior Package + Seasonal Lease renewal automations, race outreach list | Coordinator / Mike | 2026-09-07 | 2026-09-14
Weeks 11-12 | MILESTONE: Fall Tent Sale runs (Sep 18 - Oct 12) — flagship revenue event | Ownership | 2026-09-18 | 2026-10-12

## Annual Marketing Calendar
Rodgers Ski & Sport — Year 1 Marketing Calendar (Jun 2026 – Apr 2027)
Campaign / Theme | Primary Push | Prep Start | Campaign Month(s) | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027
Bike season & service | E-bike test rides, summer tune-ups, Franconia Notch tours, Scarborough bike service | Jun 2026 | Jun 2026/Jul 2026
Eastern Trail & Maine cycling | Eastern Trail Alliance tie-in, Maine Lighthouse Ride, Scarborough cycling content | Jul 2026 | Aug 2026
Summer Tent Sale | Distinct from the Fall Tent Sale — flagship summer clearance/promo event, Jul 25 - Aug 9, 2026 | Jun 2026 | Jul 25 - Aug 9, 2026
Fall Tent Sale | Flagship event: countdown, daily sale content, email sequence, Google posts | 2026-08-04 | Sep 18 - Oct 12, 2026
Boot fitting, race & Salomon exclusive | Boot Lab appointments, race-family outreach, school-team nights, Salomon race content | Sep 2026 | Oct 2026
Season kickoff: Junior Packages & Seasonal Leases | Lincoln Junior Package Program, Scarborough Seasonal Lease Program, family packages, early rentals | Oct 2026 | Nov 2026
Holiday gifting & trade-in deadline | Gift cards, apparel, accessories, service gifts, Dec 1 Junior Package trade-in reminders | Nov 2026 | Dec 2026
Mid-season tuning | Tune reminders, service tips, demo days, vacation prep | Dec 2026 | Jan 2027
School vacation week | Rentals, family programs, race-team spotlight, forgotten-gear messaging | Jan 2027 | Feb 2027
Spring skiing & bike preview | Spring-skiing content, first bike preview, service transition | Feb 2027 | Mar 2027
Season-end clearance & bike restart | Close out winter gear, reopen bike service and community ride messaging | Mar 2027 | Apr 2027

## Priorities Checklist
Rodgers Ski & Sport — Sequenced Priorities (Plan Part II)
# | Priority | Owner | Suggested Week | Status
1 | Inventory the existing assets (photos, video, logo files, customer lists, POS/rental records, press/credentials) | Coordinator | Week 1 | Done
2 | Launch the website rebuild — must go live before the Fall Tent Sale | Mike / Waterside | Weeks 1-10 | In Progress
3 | Approve initial branding: logo usage, colors, fonts, voice, tagline, templates | Mike / Ownership | Week 1 | Done
4 | Evaluate roadside signage (design, permitting, fabrication, install) | Ownership | Weeks 1-12+ | Not Started
5 | Verify Google Business Profile ownership for both locations | Ownership | Week 1 | Not Started
6 | Authorize social consolidation: one Instagram, one Facebook, one TikTok | Coordinator | Week 2 | Done
7 | Lock the promotional calendar and pricing (Tent Sale, Junior Package, Seasonal Lease, trade-in deadline) | Ownership | Week 1 | Not Started
8 | Require email capture at the register | Ownership / Stores | Week 1 (ongoing) | Not Started
9 | Approve the rental reservation workflow | Ownership / Coordinator | Weeks 5-6 | In Progress
10 | Approve core tools: email platform, Dropbox/shared files, Canva, dashboard, scheduler, analytics | Ownership / Mike | Weeks 3-4 | Done
11 | Build the Google Business operating process (weekly photos, updates, review scripts) | Coordinator | Weeks 5-6 | Not Started
12 | Launch the video content program | Coordinator | Weeks 7-8 | Done
13 | Start race-family outreach (team/coach/school list, Massachusetts race towns) | Coordinator / Mike | Weeks 7-8 | Not Started
14 | Hold a monthly 30-minute metrics review | Ownership / Mike / Coordinator | Ongoing (monthly) | Not Started